WISCONSIN WOMEN'S COUNCIL

# Status of Women Dashboard

## Power BI to Tableau rebuild — project timeline

Four gated releases, each shipped and shared before the next begins. Scope, hours and dates are grounded in the twelve existing Power BI pages and the work completed to date.

| Prepared 7 August 2026 | Availability 20–25 hrs / week | Remaining effort 46–64 hours | Target completion 29 Aug – 7 Sep 2026 |
| --- | --- | --- | --- |

## Action required before Monday

Two items gate Release 1. Neither is a build task, and every date in this document assumes both are resolved by 10 August.

| When | Item |
| --- | --- |
| By 11 Aug | Renew the Tableau licence. The trial showed 7 days remaining on 4 August, so it lapses around 11 August — during Release 1, not after it. This is the binding constraint on the whole schedule. |
| By 10 Aug | Retrieve elected_offic.xlsx from the Windows machine. The Elected Officials page cannot be built without it — the file is referenced by the workbook but absent locally. It sits inside Release 1. If it needs cleaning like the other sources, add 4–8 hours for a pipeline script. |
| 2 minutes | Spot-check one poverty measure. Sixteen measures were repointed after a field-name collision silently returned null. Confirming that Poverty Rate Female — Statewide reads 11.6% de-risks Releases 3 and 4. |

## Schedule at a glance

Both columns apply a 75% build-utilisation factor to account for meetings, context-switching and the occasional surprise.

| Release | Effort | At 25 hrs/week | At 20 hrs/week |
| --- | --- | --- | --- |
| 1 — Crime & Elected Officials | 10–16 hrs | by 15 Aug | by 17 Aug |
| 2 — Birth Count Data | 10–12 hrs | by 19 Aug | by 22 Aug |
| 3 — Demographics | 12–16 hrs | by 24 Aug | by 29 Aug |
| 4 — Occupation & Earnings | 14–20 hrs | by 31 Aug | by 7 Sep |

## Release detail

### Release 1 — Crime & Elected Officials

Target: 15 August (25 hrs/wk) or 17 August (20 hrs/wk)

| Finish Crime page — place 8 charts, wire 9 visibility zones, rebuild 9 toggle actions | 2–4 hrs |
| --- | --- |
| Polish and verify against control totals (24,963 victims / 27,848 victimizations) | 2 hrs |
| Elected Officials page — 9 charts [BLOCKED] | 4–6 hrs |
| Release QA, packaged workbook export, share, collect feedback | 2–4 hrs |
| Total | 10–16 hrs |

Blocker: Elected Officials cannot start until the source spreadsheet is recovered. If it slips, ship Crime alone and fold Elected Officials into Release 2.

### Release 2 — Birth Count Data

Target: 19 August (25 hrs/wk) or 22 August (20 hrs/wk)

| Build 11 charts — four parallel breakdowns plus headline figures | 4–6 hrs |
| --- | --- |
| Suppression handling and methodology note (449 suppressed cells) | 2 hrs |
| Layout, toggles, verify total reads 59,410 | 2 hrs |
| Release overhead | 2 hrs |
| Total | 10–12 hrs |

Watch: the four category breakdowns describe the same births from different angles — they are not additive. Summing across them multiplies the total fourfold.

### Release 3 — Demographics

Target: 24 August (25 hrs/wk) or 29 August (20 hrs/wk)

| 17 charts across four toggle sections — age, race, education, marital status | 6–8 hrs |
| --- | --- |
| Race chart using the seven additive groups (verified to total 5,914,872) | 2 hrs |
| Layout, toggles, verification | 2–4 hrs |
| Release overhead | 2 hrs |
| Total | 12–16 hrs |

Time saver: this page shares the Crime page's toggle structure exactly. Duplicate that dashboard and swap the sheets rather than rebuilding from scratch.

### Release 4 — Occupation & Earnings

Target: 31 August (25 hrs/wk) or 7 September (20 hrs/wk)

| 17 charts including the occupation and earnings-gap table | 8–10 hrs |
| --- | --- |
| Resolve the occupation label mismatch — decide upfront, not late | 2–4 hrs |
| Layout, toggles, verify against 81¢ gap and 1,447,869 women working | 2–4 hrs |
| Release overhead | 2 hrs |
| Total | 14–20 hrs |

Decision needed: only 22 of 36 earnings categories have a matching worker-count label; the other 14 will show blank earnings. Choose early — accept the blanks with a note, restrict to the 22, or split into two visuals. Deciding late means rework.

## Why this is weeks, not months

The first week of work reached roughly half of one page, but that period was almost entirely one-time setup rather than page-building. That foundation is complete and does not repeat:

- Data source — 11 tables, relationships and verified file paths

- Measures — 124 ported from Power BI's DAX and audited against source data

- Brand theme — palette, typography and background templates

- Interaction pattern — expand/collapse toggles, solved and reusable

- Bulk tooling — scripts that generate charts, buttons and actions directly

- Home page — built and styled

What remains per page is: build charts, lay out, wire toggles, verify numbers, polish.

## Accuracy improvements found during the rebuild

Five defects in the existing Power BI dashboard were identified and corrected during the port. The Tableau version is therefore more accurate than the dashboard it replaces, not simply a re-platform.

- Poverty rate for women implied 286%, caused by a broken denominator

- Four earnings measures returned blank, filtered on a value that does not exist

- Occupation counts tripled the number of working women by summing overlapping race tables

- The marital-status breakdown double-counted 60,022 people

- Census "not computed" codes were summing into charts as negative billions

## Not yet scheduled

Five further pages sit outside the four planned releases — roughly 24–36 hours, or 1.5–2.5 additional weeks at this pace.

| Page | Charts | Note |
| --- | --- | --- |
| Economic Security — poverty & SNAP | 13 | Measures already ported and corrected |
| Employment & Labour Force | 8 | Rates verified at 61.9% / 68.7% |
| Geography | 8 | Two Esri maps need rebuilding as native Tableau maps — added risk |
| Population portrait | 6 | Straightforward |
| Births overview | 4 | Pairs naturally with Release 2 |

## Assumptions and confidence

| Working availability | 20–25 hrs/week, of which roughly 75% reaches build work |
| --- | --- |
| Start date | Monday 10 August 2026 |
| Release model | Each release ships and is shared before the next begins |
| Tableau access | Uninterrupted from 10 August — at risk |
| Data availability | All sources present except Elected Officials — blocked |
| Pipeline | Python build scripts current and correct — ready |

Confidence: medium. These estimates assume the remaining pages behave like the Crime page now that the interaction patterns are solved — reasonable, since they use the same mechanics and the same data source. If a page raises a genuinely new Tableau problem, as dynamic visibility and parameter actions each did, add 2–4 hours for that page.

Status of Women Dashboard — rebuild timeline · Prepared 7 August 2026